# IT Project Guidance

Development Effort Estimation

Version:

0.4

## Purpose

This guidance describes commonly used estimation methodologies for technology projects and provides practical recommendations for their use in public sector environments.

The objective is to reduce estimation error so that projects are less likely to fail across one or more delivery axes: cost, schedule, delivered capability, or realised value.

Estimation discipline improves budgeting accuracy, reduces governance disruption, and supports responsible use of public funds.

## Synopsis

Technology delivery requires estimating the effort needed to design, build, integrate, deploy, and operate systems. Estimation errors frequently contribute to project overruns or reduced delivery value.

Several estimation methodologies exist. Some attempt to measure the functional size of a system independent of technology, while others estimate work relative to previously completed tasks.

Over time many organisations shifted toward lightweight estimation methods associated with Agile delivery practices. These approaches are effective for team-level planning but often provide limited support for early budgeting or programme-level governance.

Formal size-based estimation techniques such as Function Point Analysis and COSMIC Functional Size Measurement remain technically sound but require trained analysts and historical productivity data to deliver their full value.

In environments where delivery teams change frequently, such as many public sector projects, these methods may not provide precise effort prediction. However they remain valuable analytical tools for understanding system scope and informing higher-level estimation approaches.

# Executive Summary

Accurate estimation is one of the most challenging aspects of technology delivery.

Historically, estimation methodologies were developed to measure the functional size of software systems so that effort could be predicted more reliably.

Methods such as Function Point Analysis and COSMIC Functional Size Measurement allow organisations to quantify the amount of functionality a system must provide. When combined with historical productivity metrics, these methods can produce relatively accurate effort estimates.

In practice, many modern development environments have adopted lightweight estimation techniques such as story points or T-shirt sizing. These approaches are simple and collaborative but often lack the analytical rigour needed for early project budgeting.

Government environments introduce additional constraints. Public funding is typically allocated through annual or multi-year appropriations approved in advance. Projects therefore require credible estimates before delivery begins.

Formal estimation methods remain relevant in such environments, but the frequent use of different suppliers and delivery teams can limit the availability of consistent productivity data.

A pragmatic approach is therefore recommended. Structured estimation techniques should be used to analyse system scope, while lightweight estimation approaches can translate this understanding into practical delivery plans.

## Contents

Purpose	1

Synopsis	1

Executive Summary	2

Contents	3

Background and Context	5

Public Sector Funding Constraints	5

Estimation Methodologies	6

Function Point Analysis	6

COSMIC Functional Size Measurement	6

Use Case Points	6

Agile Relative Estimation	7

Flow-Based Estimation	7

Recommendation	8

Recommendation for Project Teams	8

Recommendation for Agencies	8

Conclusion	8

Appendices	11

Appendix A - Document Information	11

Versions	11

Images	11

Tables	11

References	11

Review Distribution	11

Audience	12

Diagrams	12

Acronyms	12

Terms	12

Appendix B – Function Point Analysis Practical Guide	13

Appendix C - COSMIC Analysis Practical Guide	14

Appendix D –  Using COSMIC to Inform Agile Estimation	14

Overview of the Approach	15

Step 1 – Identify Functional Processes	15

Example	15

Step 2 – Count Data Movements	15

Example – Teacher Leave Funding System	16

Step 3 – Calculate Functional Size	17

Step 4 – Map Functional Size to Size Bands	17

Step 5 – Convert to T-Shirt Estimate	18

Environmental Adjustment	18

AI-Assisted Analysis	18

Benefits of the Hybrid Approach	18

# Background and Context

Estimation is the process of predicting the effort required to deliver a system capability.

Reliable estimation supports budgeting, procurement, planning, and governance oversight. Poor estimation can lead to delays, cost overruns, scope reduction, or diminished delivery value.

Software estimation has historically been difficult because system requirements evolve during development and technical complexity may not be fully understood early in a project.

Formal estimation techniques were therefore developed to improve prediction accuracy. These approaches attempt to measure the functional size of a system independently of the technology used to implement it.

Two widely recognised techniques are Function Point Analysis and COSMIC Functional Size Measurement. These methods quantify the functional interactions between users, systems, and persistent data.

In organisations that maintain long-term productivity records, functional size measurement allows effort estimates to be derived from historical performance data.

However many public sector projects are delivered by changing teams, suppliers, and delivery partners. When productivity data is not consistent across projects, the ability to predict effort from functional size alone is reduced.

## Public Sector Funding Constraints

Government technology projects operate within funding structures that differ significantly from commercial environments.

For example, in New Zealand, public sector initiatives are commonly funded through appropriations approved as part of the Government Budget process. These appropriations are authorised before delivery begins and typically remain fixed during the funding period.

Unlike commercial organisations, government agencies cannot easily validate investment assumptions through early product sales or staged market expansion.

Additional funding during delivery is rarely available without formal reprioritisation or new budget approval.

These constraints make credible estimation particularly important in government environments.

# Estimation Methodologies

## Function Point Analysis

Function Point Analysis measures the functional size of a system by counting interactions between users and the system.

The analyst first defines the boundary of the system. Interactions with external users or systems are then identified and classified as inputs, outputs, or inquiries. Persistent data structures maintained by the system are identified as internal logical files, while data managed by external systems is classified as external interface files.

Each identified element is assigned a complexity weight based on the number of data elements involved. The weighted values are combined to produce a functional size expressed in function points.

Effort estimates can then be derived by multiplying the number of function points by historical productivity metrics.

An advantage of this approach is that it produces a technology-independent measure of system functionality. A consideration is that the method requires trained analysts and careful interpretation of requirements. A disadvantage is that it can be time-consuming and less suited to early project estimation when requirements are incomplete.

## COSMIC Functional Size Measurement

COSMIC measures software size by counting movements of data between users, system processes, and persistent storage.

The system boundary is first defined. Functional processes triggered by external events are then identified. Each process is analysed to identify the number of data entries, data exits, data reads from persistent storage, and data writes to persistent storage.

Each data movement represents one COSMIC functional unit. The total number of units represents the functional size of the system.

Effort can be estimated by applying historical productivity metrics that relate COSMIC units to development effort.

An advantage of COSMIC is that it aligns well with modern service-based architectures and distributed systems. A consideration is that practitioners must understand the COSMIC counting model to apply it consistently. A disadvantage is that the method can appear complex to teams unfamiliar with formal estimation techniques.

## Use Case Points

Use Case Points estimate system size by analysing the number and complexity of use cases and actors.

The estimator identifies system actors and classifies them by complexity. Use cases are then analysed based on the number of interactions or steps they contain. These values are combined to produce a baseline size estimate.

The baseline estimate is then adjusted using technical and environmental complexity factors to account for system characteristics such as performance constraints or distributed processing.

An advantage of this method is that it aligns naturally with requirements expressed as use cases. A consideration is that the accuracy of the estimate depends on the quality and completeness of the use case documentation. A disadvantage is that the method can produce unreliable estimates when requirements are poorly structured.

## Agile Relative Estimation

Agile estimation techniques estimate work relative to previously completed work items rather than measuring functional size directly.

The team selects a baseline work item and assigns it a reference size. Additional work items are estimated relative to this baseline using categories such as small, medium, large, or numerical story point values.

Teams commonly use collaborative techniques such as planning poker to reach consensus on the relative size of each work item.

An advantage of relative estimation is that it is simple and fast to apply. A consideration is that estimates are specific to the team performing the work and cannot easily be compared across teams. A disadvantage is that relative estimates often expand significantly when estimating larger scopes such as epics or projects.

## Flow-Based Estimation

Flow-based estimation predicts delivery capacity based on observed team performance rather than estimating individual work items.

Teams track metrics such as throughput, cycle time, and lead time. Future delivery timelines are predicted based on these historical patterns.

An advantage of this approach is that it relies on observed performance rather than speculative estimation. A consideration is that it works best for stable teams performing similar work over time. A disadvantage is that it provides limited support for estimating entirely new systems.

# Recommendation

## Recommendation for Project Teams

Project teams should adopt estimation approaches that balance analytical discipline with practical usability.

Relative estimation techniques such as T-shirt sizing or story points should be used for day-to-day planning and iteration management.

However these estimates should be informed by structured analysis derived from functional sizing methods such as COSMIC or Function Point Analysis. Analysts should identify functional processes, data interactions, and external interfaces before assigning relative sizes.

This structured approach improves estimation quality by ensuring that significant functional areas are not overlooked during estimation.

## Recommendation for Agencies

Public sector agencies should strongly consider building institutional knowledge about software estimation over time.

Even when projects are delivered by different suppliers, agencies can maintain records of estimated functional size and actual delivery effort across projects.

Over time this information can produce productivity benchmarks that allow functional sizing methods to become more predictive.

Developing such datasets gradually improves estimation accuracy and strengthens governance oversight of public technology investment.

# Conclusion

Estimation accuracy is essential for effective technology governance.

Lightweight estimation techniques dominate modern software development, but government projects benefit from structured approaches that encourage deeper understanding of system scope.

Formal estimation techniques such as Function Point Analysis and COSMIC Functional Size Measurement remain valuable analytical tools even where historical productivity benchmarks are unavailable.

Combining structured analysis with simple estimation techniques provides a balanced approach that improves planning accuracy while remaining practical for project teams.

Appendices

Appendix A - Document Information

Authors & Collaborators

- Sky Sigal, Solution Architect

### Versions

  - Initial Draft

  - Corrections

  - Added Appendices

  - Added Appendix D

### Images

No table of figures entries found.

### Tables

No table of figures entries found.

### References

Standish Group International. CHAOS Report Series.

COSMIC Consortium. COSMIC Functional Size Measurement Method.

International Function Point Users Group. Function Point Counting Practices Manual.

Project Management Institute. Pulse of the Profession.

Forsgren, Humble, Kim. Accelerate: The Science of Lean Software and DevOps.

### Review Distribution

The document was distributed for review as below:

| Identity | Notes |
| --- | --- |
| Duncan Watson, Enterprise Architect |  |
| Andrew Win, Lead Analyst |  |
| Kylie Keen, Business Analyst |  |
| Dan Young, Lead Developer |  |
| Peter Martin, Lead Developer |  |

### Audience

The document is technical in nature, but parts are expected to be read and/or validated by a non-technical audience.

### Diagrams

Diagrams are developed for a wide audience. Unless specifically for a technical audience, where the use of industry standard diagram types (ArchiMate, UML, C4), is appropriate, diagrams are developed as simple “box & line” monochrome diagrams.

### Acronyms

API

: Application Programming Interface.

BUST

: IIBA derived acronym for IT service analysis – Business, User, System (Functional and Quality), and Transitional

DS-BUST-O

: a fuller acronym for Drivers, Stakeholders, Business, User, System (Functional and Quality), Transitional and Operational Requirement development artefacts.

DDD

: Domain Driven Design

FP

: Function Point, a method of analysis

GUI

: Graphical User Interface. A form of UI.

IIBA

: International Institute of Business Analyse

IT

: acronym for Information, using Technology to automate and facilitate its management.

UI

: User Interface. Contrast with API.

### Terms

Refer to the project’s Glossary.

Application Programming Interface

: an Interface provided for other systems to invoke (as opposed to User Interfaces).

Capability

: a capability is what an organisation or system must be able to achieve to meet its goals. Each capability belongs to a domain and is realised through one or more functions that, together, deliver the intended outcome within that area of concern.

Domain

: a domain is a defined area of knowledge, responsibility, or activity within an organisation or system. It groups related capabilities, entities, and functions that collectively serve a common purpose. Each capability belongs to a domain, and each function operates within one.

Entity

: an entity is a core object of interest within a domain, usually representing a person, place, thing, or event that holds information and can change over time, such as a Student, School, or Enrolment.

Function

: a function is a specific task or operation performed by a system, process, or person. Functions work together to enable a capability to be carried out. Each function operates within a domain and supports the delivery of one or more capabilities.

ISO-25022

: identifier of standard based Qualities Users experience when using a systems, which in turn relies on ISO-25012, therefore ISO-25010.

ISO-25012

; identifier of standard based Qualities of System Data, which is in turn reliant on ISO-25010.

ISO-25010

: identifier of Standard based Qualities of Systems

Person

: a physical person, who has one or more Personas. Not necessarily a system User.

Persona

: a facet that a Person presents to a Group of some kind.

Quality

: a quality is a measurable or observable attribute of a system or outcome that indicates how well it meets expectations. Examples include reliability, usability, and performance. Refer to the ISO-25000 SQuaRE series of standards.

User

: a human user of a system via its UIs.

User Interface

: a system interface intended for use by system users. Most computer system UIs are Graphics User Interfaces (GUI) or Text/Console User Interfaces (TUI).

Appendix B – Function Point Analysis Practical Guide

Function Point Analysis measures the functional size of software based on interactions between users and the system.

Define the system boundary and identify external actors interacting with the system.

Identify functional transactions including external inputs, outputs, and inquiries. Inputs represent data entering the system. Outputs represent processed data leaving the system. Inquiries represent simple data retrieval operations.

Identify persistent data structures. Internal logical files represent data maintained by the system. External interface files represent data maintained by external systems but used by the application.

Assign complexity values based on the number of data elements and referenced files involved in each transaction.

Sum the weighted counts to produce the total number of function points.

Use historical productivity metrics to estimate development effort from the total function point count.

Appendix C - COSMIC Analysis Practical Guide

COSMIC measures software size by counting data movements.

Define the boundary of the system being analysed.

Identify functional processes triggered by external events such as user requests or system messages.

For each process count the number of entries where data enters the system, exits where data leaves the system, reads where data is retrieved from persistent storage, and writes where data is stored.

Each data movement represents one COSMIC functional size unit.

Sum all data movements across all functional processes to produce the total COSMIC functional size of the system.

Effort estimates can then be derived using productivity metrics relating COSMIC size to development effort.

AI tools may assist in identifying candidate processes and data movements from requirements or API specifications, but human validation remains necessary to confirm system boundaries and functional interpretations.

Writing accuracy review

The statement that formal estimation methods remain valid but require historical productivity data is accurate.

The description of New Zealand government funding cycles is broadly correct, though agencies can sometimes request reprioritisation or supplementary funding.

The claim that COSMIC aligns better with modern service architectures is widely supported in software engineering literature.

Appendix D –  Using COSMIC to Inform Agile Estimation

Formal functional size measurement methods such as COSMIC can provide analytical structure when estimating system scope. However, where delivery teams change frequently and historical productivity data is unavailable, COSMIC estimates cannot reliably predict development effort.

In these situations COSMIC can still be used to structure thinking about system complexity. The resulting functional size estimate can then inform Agile relative estimation techniques such as T-shirt sizing.

### Overview of the Approach

The approach involves five steps.

Identify functional processes triggered by external events.
Count the associated COSMIC data movements.
Calculate the total functional size.
Map the size to a relative complexity band.
Convert the band into a T-shirt estimate used for delivery planning.

### Step 1 – Identify Functional Processes

Functional processes represent system behaviour triggered by external events.

In government systems these processes often include more than the primary business function. Supporting activities such as authentication, authorisation, document handling, and notification flows frequently represent a significant portion of system complexity and should be included in the analysis.

#### Example

For example, a teacher leave replacement funding system may contain the following processes.

Submit leave funding request
Upload supporting evidence
Validate user identity
Verify school authority to submit claim
Calculate funding eligibility
Review claim
Approve or reject claim
Send notification messages
Recalculate claims when rules change

### Step 2 – Count Data Movements

For each functional process identify the COSMIC data movements.

Entry – data entering the system
Exit – data leaving the system
Read – data retrieved from persistent storage
Write – data stored in persistent storage

Each movement counts as one COSMIC functional size unit.

#### Example – Teacher Leave Funding System

Submit Leave Funding Request
Entry – claim submitted by school
Read – retrieve teacher employment record
Read – retrieve leave rules
Write – store claim record
Exit – confirm submission
Total: 5 units

Upload Supporting Evidence
Entry – upload evidence metadata
Write – store document reference
Read – retrieve claim record
Exit – confirm upload
Total: 4 units

Validate User Identity
Entry – authentication request
Read – retrieve identity record
Exit – authentication result
Total: 3 units

Verify School Authority
Entry – authorisation request
Read – retrieve role information
Read – retrieve employment record
Exit – verification result
Total: 4 units

Calculate Eligibility
Entry – calculation request
Read – retrieve claim data
Read – retrieve funding rules
Write – store calculated value
Exit – return calculation result
Total: 5 units

Review Claim
Entry – reviewer request
Read – retrieve claim record
Read – retrieve evidence metadata
Exit – display claim
Total: 4 units

Approve or Reject Claim
Entry – reviewer decision
Read – retrieve claim
Write – update claim status
Exit – notify school
Total: 4 units

Send Notification
Entry – notification trigger
Read – retrieve contact details
Exit – send email
Total: 3 units

Recalculate Claims
Entry – rule change event
Read – retrieve claims
Read – retrieve updated rules
Write – update calculations
Exit – notify administrators
Total: 5 units

### Step 3 – Calculate Functional Size

Submit request: 5
Upload evidence: 4
Validate identity: 3
Verify authority: 4
Calculate eligibility: 5
Review claim: 4
Approve or reject: 4
Send notification: 3
Recalculate claims: 5

Total functional size: 37 COSMIC units

### Step 4 – Map Functional Size to Size Bands

Very Small: 1–10 COSMIC units
Small: 10–30 COSMIC units
Medium: 30–80 COSMIC units
Large: 80–200 COSMIC units
Very Large: more than 200 COSMIC units

In this example the capability falls within the Medium band.

### Step 5 – Convert to T-Shirt Estimate

Very Small → XS
Small → S
Medium → M
Large → L
Very Large → XL

The example capability would therefore be estimated as Medium.

### Environmental Adjustment

COSMIC estimates represent functional development effort only. Government delivery environments often introduce additional effort due to governance processes, operational workload, integration dependencies, and limited resource availability.

For this reason delivery duration may be several times greater than the pure development effort. In many public sector environments the effective delivery multiplier commonly ranges between three and six times the estimated development effort.

These adjustments reflect organisational constraints rather than software complexity and should be documented separately from the functional estimate.

### AI-Assisted Analysis

AI tools can accelerate COSMIC analysis by identifying candidate functional processes and data movements from requirements or service descriptions.

For example:

“Given the following system description, identify functional processes and list COSMIC entries, exits, reads, and writes for each process.”

The resulting analysis should then be reviewed by a practitioner to confirm system boundaries and functional interpretations before counting the final COSMIC units.

### Benefits of the Hybrid Approach

Using COSMIC analysis to inform Agile estimation combines the strengths of both methods. Functional analysis improves understanding of system scope, while relative estimation techniques allow teams to convert that understanding into practical delivery plans.

This approach reduces the risk of overlooking supporting system behaviour such as identity verification, document management, or workflow processing while maintaining a simple estimation process suitable for delivery teams.