## INSTRUCTIONS
PURPOSE:
New employees or contractors who have not previously had experience working in an organisation tasked with delivering projects for managing public records government purposes may have a limited understanding of the context in which we are regulated and obligated to operate.
CONTEXT:
Projects to deliver Services using IT Services have a high chance of failure (66+%). The following are a number of common preventable key causes:
- Not discovering who the system is for (the [full] audience)
- Not discovering what they desire (their stated needs)
- Not using SMEs in each domain to define targe objectives, rather than guessing what they probably want
- Not collecting the Desires of SMEs beyond Business needs, forgetting it takes a village to operate and deploy a service and operate it over 7+ years
- Not discovering where they conflict with other's desires, and re-looking for a solution that best meets multiple parties' needs
- Not rethinking their Desires & Processes to develop what is *possible* in a ditigal environment - rather than blindly encoding *current* behaviours
- Not converting the collected Desires into Defined S.M.A.R.T. Objectives as Requirements
- Not sequencing effort in an order that decreases risks, issues, rework, expense - AND gets something out the door to PROD-DATA every 2 weeks
- Priotising effort unevenly to focus on the needs of one group (generally Business) above all others (generally Operations), impacting Users
- Not getting organised Governance of both Business and Technical decisions from the start
- Putting off meeting governance reporting and and endorsement obtaining steps till too late, impacting scheduling
- Focusing on the Development phase, rather than the Operations and User Support phases, and working back to developing to meet its needs
- Hiring and following inappropriate guidance by resources with the capabilities to perform specialised tasks -- but not reduce service delivery risk
- Blindly following organisation procurement guidelines, and choosing a system that doesn't have the capability by itself, and can't be customised later to deliver functionality expected by stakeholders
THIS DOCUMENT:
Addresses a couple of the above common causes of project failure by capturing early the Desires of multiple stakeholders roles -- each within their own tab -- so that everybody is aware of each others Desires and can work towards a common objective. The Desires were collected from Stakeholder Roles involved with Operating the service for a service life span (7+ years), working all the way back to listing the Stakeholder Roles required to iteratively get there (Direction, Discovery, Definition, Design, Deployment, Development, Monitoring, Operating, Improving, Supporting, Decommissioning).
AUDIENCE:
Small projects do not have the resources for each Role -- generally a single resource/person is fulfilling multiple Roles, often over-committed. But Roles permit planning, and a plan is better than no plan.
Larger projects may have more resouces, but often will be under-committed (eg: only 50%) with a lot of time used to synch tasks across Roles.
INSTRUCTIONS:
- Use the TOC to select the Tab that best fits your Role
- The Default Order for each Table is on the CONCERN.ID column
- Read the definition of the Role, it's primary Tasks, and then it's Deliverables, Responsibilities, and Guidance
- Read the definition of other person's Roles, Tasks, Deliverables, Responsibilities, and Guidance, to better understand their Perspectives
- Correlate the Desires to default contractual Requirements supplied by the Organisation, and any Project specific contractual Requirements
- When developing project work items, consider these Desires in the background
- One can use the Table as is, or use Word's MailMerge functionality to develop Document parts as needed
- System Design Requirements do delve down to detail that is not required on all projects (Filter on the ID column using variations of ????.000)
NOTES:
- Improve: if a Stakeholder Role Group is missing, or their Desires are not listed, flag it for adding or consolidating. Don't remove Desires.
- Format: Each entry loosely follows traditional User Story format, bar the change from an American heavy "I Want" to a more discussible ", I Desire"
- "Desire": the term was intentionally chose...for want of a better word. It implies it's *not* a firm (Contractual) requirement yet -- it's still up for Discussion (as to how it adds value compared to other stakeholder's Desires, and whether it negatively impacts others). "I Want" was too boisterous. "I Wish" implied it was a fairy tale outcome, "I Need" was incorrect. I Lust For was a bit too OTT.
- "Organisation": where possible, each entry's wording is intentionally abstracted to be useable within any Organisation (rather than this one specifically) to more easily determine whether the project approach and system design follow industry standards and norms or not. Deviation from Norms CAN be a strong warning of Risk (but also is not always the case).
- UID: Each entry's UID is purposeful in that instead of it being developed to be a sequential run (eg: REQ-0001 to REQ-00125) pointing to different statements in every project, the UID's encoding of Stakeholder, Purpose, and Order such that the they ensure uniqueness and reusable across projects
- Paired: one role's Desired outcome is another role's Responsibility. Check to see that both aspects are captured in this catalogue. Thank you.
- Generic: as per the title of the Document, these are *Generic* Desires that are applicable to the vast majority of current IT projects. On top of them a project develops a particular project's specific Desires (generally this is limited to just capturing additional Business and Business SUpport stakeholder Desires.
- Excel: Although Excel is not a DB, or RowShare, or AirTable --it's the most widely available tool. Sigh. Deal with it.
- Use: Word's MailMerge functionality to develop document fragments from one table or another. See previous point.
- Corrections:Spelling is important -- but less important for now than Intent/Usefulness (i.e. don't sweat the small stuff -- but flag errors them when you see them).
FINAL WORDS:
Good luck with your project.
- IT projects are complex -- but not complicated. After 60 years it is actually (contrary to hype) more of a skilled career -- even if unregulated -- than an art form, so if you do follow well-trodden automated delivery, system, component and code patterns, you *will* keep delivery organised & achievable.
- Don't fall into the trap of delivering an MVP (which too often ends up standing for Missing Valuable Planning). Aim for delivering early and iteratively improving a Minimum Viable Service (MVS) -- which encodes early the concept that the service has a long lifespan, needs monitoring, maintenance, bau development & improvement, operations, support.
- Advernturers dream of getting to the North or South Pole, the Amazon or El Dorado. And you never hear of them again except in children's books. Successful Explorers don't plan to get there (the exciting scary Dev part) -- they plan to get back to deliver the value (Operating), and work back from the end all the way back to where they have to start. what resources are needed at way stations, etc. Roald Amundsen called Adventures Piss Poor Planned Projects (or something to that effect). He survived. Robert F. Scott froze and didn't deliver. You can learn a lot from Roald's studying, planning, partnering, teaming, and traveling light. He also used dogs (the Automation of the day), rather than pulling sleds with humans, as Scott did.
- Bet on Automation every time. It encodes Definition, Development, Deployment and QA IP such that its available over the whole Operation time, protecting it from being lost due to resources leaving at the end of the Capex period. And makes light work of repetitive work to free thinking for other tasks.
- Don't believe the hype. Agile never recommended "Start Dev'in, no Planning or Documentation needed." It recommending relying on JUST ENOUGH Documentation needed to communicate the Planning. And NEVER said skip the Planning. Planning is the most efficient way to measure twice, cut once, cost less, be more predicatable in terms of effort, schedule, expense. Use Agile work management to meet the demands of the plan.
- If you let Developers plan your service or system, rather than stick to Developing to Architected plans, more fool you. Can't say you were not warned. That's like asking your great plumber to design your house. Different skillsets are required to plan the placement, the orientation, the driveway, waste, storm water, electricity, heating, ventilation, lighting, glazing, wall structure, cladding, insulation, lining, openings, triming, painting, joists, floors, stair slopes, railings, wet areas lining, tiling, kitchen and bathroom cabinetry -- all within neighbourhood, regional, national, international standards, agreements, and obligations, and need to coordinate with traffic specialists, earthworks specialists, solar specialists. etc. The same applies in that you wouldn't ask your electrician either, or your painter, nephew, or best buddy to do all that either, no matter how good they are in their vertical field. (Then again, I guess you can do it -- if its your personal morgage -- rather than a budget from shared treasury).
- Careful as to choose architects appropriate for the objectve. There are differences in between internal employee facing architects, and architects of services for customers. Few are good at both -- and the services they will propose will generally be appropriate for only one arena. Architects that do houses, for example, generally do poor restaurants, hotels and commercial spaces -- and architects that do the later generally make homes that feel industrial, using industrial solutions for lighting, fixtures, bathroom dimensions, surfaces. The same for software: enterprise facing architects may opt for rules, regulations and order, cost and queling disent -- whereas customers are best served with flexibility, unique circumstances, social media, feedback, and decisions based on other factors than cost.

## TOC
SEQUENTIAL TABLE OF CONTENTS | ROLE DESCRIPTION
Roles of those who get projects started:
Sponsor | #REF!
Business Case Developer | #REF!
Roles of those who govern project starting, continuance or cancellation:
ITC Governance Board | #REF!
Project Governance Board | ='DESIRES-PROJECT-GOVERNANCE'!A5
Roles of those who direct projects and report to governance:
Program/Project Manager | #REF!
Roles of those who organise project effort:
Effort Coordinator (ScrumMaster) | #REF!
Roles of those who provide Endorsements Required at different times:
Legal Services | #REF!
Privacy Services | #REF!
Māori Services | #REF!
Information Services | #REF!
Data Services | #REF!
C&A Security Services | #REF!
Technical Security Services | #REF!
Roles of those who keep services working for 10+ years:
Deployment Services | #REF!
Monitoring Services | #REF!
Maintenance Services | #REF!
Support Development Services | #REF!
Operations Services | #REF!
Roles of those who take care of users:
Support Users (General Customer) | #REF!
Support Users (Business) | #REF!
Roles of those who use the service:
Users (Internal Business Providers) | #REF!
Users (Public Service Consumers) | #REF!
Operations Services | #REF!
Roles of those who design the services:
Consumer Architecture Services | #REF!
Business Archtiecture Services | #REF!
Enterprise Architecture Services | #REF!
Solution Architecture Services | #REF!
Technical Architecture Services | #REF!
Client User Interface Experience Design Services | #REF!
Roles of those who provide the procured/subscribed to services:
Vendor Service Provider | #REF!
Roles of those who capture and organise competing stakeholder desires:
Business Analysis Services | #REF!
Stakeholder Analysis Services | #REF!
Quality Analysis Services | #REF!
Roles of those who develop how the service functionality is made accessible:
UI Design | #REF!
Roles of those who develop, customize, integrate the solution's services:
Development - Pipeline | #REF!
Development - QA Automation | #REF!
Development - Service | #REF!
Development - Service APIs | #REF!
Development - Service API Client | #REF!
Development - Website | #REF!
Development - Service Client | #REF!
Development - ETL | #REF!
Roles of those who develop, customize, integrate the service content:
Development - Māori Content | #REF!
Development - Content | #REF!
Roles of those who Endorse the Design, Development, Processes:
Technical Design Review Board | #REF!
C&A Services | #REF!
Change Control Role | #REF!
Change Advisory Board | #REF!
Roles of those who Accept the Residual Risks to the Business Group And wider Organisation:
Sponsor | #REF!
CIO/CDO | #REF!

## REF-LOOKUPS
Status | Environment | Type | MAJOR (PHASE): | MINOR(DELIVERABLE): | STAKEHOLDERS | TYPE | DESIRE TYPE
Draft | Undefined | Undefined | P00.--- | D000.--- | S00.Unclassified | T0.--- | DT00.Role Purpose
Reviewable | Unknown | Unknown | P00.Procurement | D001.SOW | S00.Procurement | T1.Objectives | DT10.Prerequisites: Setup
Rejected | Cloud/SaaS | Service | P01.Destination | D002.SOW/Delivery Management Services | S01.ALL | T2.Deliverables | DT20.Prerequisites: Info
Accepted | Cloud/PaaS | Configurable | P02.Dependencies | D003.SOW/Stakeholder Analysis Services | S02.CEO | T3.Task | DT30.Deliverables: Final
Active | Cloud/CaaS | Customizable | P03.Governance | D004.SOW/Design Services/Architecture | S03.Organisation Strategic Alignment Governance | T4.Milestone | DT40.Deliverables: Enabling
Replaced | Cloud/IaaS | Custom | P04.Direction | D005.SOW/Design Services/UX | S04.Organisation Information Governance | T5.Constraints | DT50.Tasks
Retired | OnPrem/IaaS |  | P05.Delegation | D006.SOW/ScrumMaster Services | S05.Organisation Legal Governance | T6.Specs:Qualities | DT60.Responsibility
|  |  | P06.Discovery | D007.SOW/QA Analysis Services | S06.Organisation Probity Governance | T7.Specs:Functionality | DT70.Guidance
|  |  | P07.Desires | D008.SOW/C&A Services | S07.Organisation Privacy Governance | T8.Specs:Guidance | DT80.Desires
|  |  | P08.Definition | D009.SOW/Delivery Services | S08.Organisation Comms Governance | T9.Assumptions
|  |  | P09.Procurement | D010.SOW/Infrastructure Services | S09.Organisation Change Management Governance
|  |  | P10.Design | D011.SOW/Monitoring Services | S10.---
|  |  | P11.Detailed Design | D012.SOW/Operations Services | S11.---
|  |  | P12.Technical Design | D013.SOW/Data Migration Services | S12.---
|  |  | P13.Content Design | D014.SOW/Resource & Content Services | S13.Business Sponsor
|  |  | P14.QA Definition | D015.SOW/Media Interpretation Services | S14.Business Governance
|  |  | P15.Delivery | D016.SOW/Development Services/Pipeline | S15.Business Content Governance
|  |  | P16.Development | D017.SOW/Development Services/QA Automation | S16.---
|  |  | P17.Driving | D018.SOW/Development Services/Server | S17.---
|  |  | P18.Decommissioning | D019.SOW/Development Services/Client/UX | S18.ITC CIO/CDO
|  |  |  | D020.SOW/Development Services/Data | S19.ITC Data Integration Governance(ITC-DIGI)
|  |  |  | D021.SOW/Security Review Services | S20.ITC Technology Investments Alignment Governance(ITC-DA/GB)
|  |  |  | D022.SOW/Support Services | S21.ITC Technology Investments Alignment Governance(DA)
|  |  |  | D023.SOW/Training Services | S22.ITC Architecture Alignment Governance(ITC-TWG)
|  |  |  | D024.--- | S23.ITC Design Security Services
|  |  |  | D025.--- | S24.ITC Certificate & Assurance (C&A) Services(C&A)
|  |  |  | D031.Business | S25.ITC Change Governance(CAB)
|  |  |  | D032.Business/Options Analysis | S26.---
|  |  |  | D033.Business/Stakeholders Map | S27.---
|  |  |  | D034.Business/HL Objectives | S28.Users/Public
|  |  |  | D035.Business/Gap Analysis | S29.Users/Authenticated
|  |  |  | D036.Business/Case | S30.Users/Service Consumers
|  |  |  | D037.Business/Delivery Plan | S31.Users/Service Providers (Frontline)
|  |  |  | D038.Business/Change Management Plan | S32.Users/Business Services (Coordinators)
|  |  |  | D039.Business/Change Comms Plan | S33.Users/Training Services
|  |  |  | D040.Business/Execution Plan | S34.Users/Support Services (General)
|  |  |  | D041.Business/Requirements Tracability Report | S35.Users/Business Service (Support)
|  |  |  | D042.--- | S36.Users/Operations (Configuration)
|  |  |  | D043.--- | S37.---
|  |  |  | D101.Governance Reporting | S38.---
|  |  |  | D102.Governance Reporting/Risks | S39.Partners
|  |  |  | D103.Governance Reporting/Issues | S40.API Gateway Services
|  |  |  | D104.Governance Reporting/Technical Debt | S41.Analytics Services
|  |  |  | D105.Governance Reporting/Resources | S42.Data warehouse Services
|  |  |  | D106.Governance Reporting/Effort | S43.Archiving Services
|  |  |  | D107.Governance Reporting/Functionalities | S44.---
|  |  |  | D108.Governance Reporting/Qualities | S45.---
|  |  |  | D109.Governance Reporting/Quality Assurance | S46.Delivery Management Services
|  |  |  | D110.Governance Reporting/Endorsements | S47.Business Case Consultant Services
|  |  |  | D111.Governance Reporting/Deliverables | S48.Enterprise Architecture Services
|  |  |  | D112.--- | S48.Stakeholder Analysis Services
|  |  |  | D113.--- | S49.Solution Architecture Services
|  |  |  | D251.Classification | S50.Design Services/UX
|  |  |  | D252.Classification/Information Category | S51.---
|  |  |  | D253.Classification/Privacy (PTA) | S52.---
|  |  |  | D254.Classification/Risk (STA) | S53.Design Security Review Services
|  |  |  | D254.--- | S54.---
|  |  |  | D255.--- | S55.---
|  |  |  | D261.C&A | S56.ScrumMaster Services
|  |  |  | D262.C&A Risk (ST2) | S57.QA Analysis Services
|  |  |  | D263.C&A Risk Audit | S58.Identity Services
|  |  |  | D264.--- | S59.Data Services
|  |  |  | D265.--- | S60.Deployment Services
|  |  |  | D271.Endorsement | S61.Infrastructure Services
|  |  |  | D272.Endorsement/ITC-GB | S62.Monitoring Services
|  |  |  | D273.Endorsement/ITC-DA | S63.Security Services
|  |  |  | D274.Endorsement/ITC-QA | S64.Maintenance Services
|  |  |  | D275.Endorsement/ITC-C&A | S65.Operations Services
|  |  |  | D276.Endorsement/ITC-CAB | S66.Data Migration Services
|  |  |  | D277.--- | S67.BAU Development Services
|  |  |  | D278.--- | S68.Support Services
|  |  |  | D301.Endorsement/ITC-Security at CAB | S69.Training Services
|  |  |  | D302.Endorsement/ITC-Infrastructure at CAB | S70.---
|  |  |  | D303.Endorsement/ITC-Monitoring at CAB | S71.---
|  |  |  | D304.Endorsement/ITC-Maintenance at CAB | S72.Resource & Content Services
|  |  |  | D305.Endorsement/ITC-Operations at CAB | S73.Interpretation Services
|  |  |  | D306.Endorsement/ITC-Deployment at CAB | S74.---
|  |  |  | D307.Endorsement/ITC-Support at CAB | S75.Development Services
|  |  |  | D308.Endorsement/ITC-Training at CAB | S76.Development Services/Pipeline Automation
|  |  |  | D309.Endorsement/ITC-Identity at CAB | S77.Development Services/QA Automation
|  |  |  | D310.Endorsement/ITC-Legal at CAB | S78.Development Services/Server
|  |  |  | D310.--- | S79.Development Services/Specialist Integration
|  |  |  | D311.--- | S80.Development Services/Client/UX
|  |  |  | D331.Provisioning | S81.Development Services/ETL
D332.Provisioning/Identities
D333.Provisioning/Workstations
D334.Provisioning/Comms
D335.Provisioning/Prod. Tools
D336.---
D337.---
D341.Subscriptions
D342.Subscriptions/ALM Hub
D343.Subscriptions/Infrastructure
D344.Subscriptions/DNS
D345.Subscriptions/Certs
D346.Subscriptions/WebsiteUpCheck
D347.Subscriptions/Email
D348.Subscriptions/Validation
D349.Subscriptions/Search
D350.Subscriptions/GeoIP
D351.Subscriptions/Addresses
D352.---
D353.---
D361.Specifications
D362.Specifications/Info/Entities
D363.Specifications/Info/Classification
D364.Specifications/REQ/Functional
D365.Specifications/REQ/Quality
D366.Specifications/REQ/Technical
D367.Specifications/AccessMatrix
D368.Specifications/REQ/System (F+Q)
D360.---
D361.---
D371.Architecture
D372.Architecture/SAD
D373.Architecture/TDD
D374.---
D375.---
D381.Documentation
D382.Documentation/Specifications
D383.Documentation/StyleGuide
D384.Documentation/Infrastructure
D385.Documentation/Configuration
D386.Documentation/Data Schema
D387.Documentation/Integration
D388.Documentation/Deployment
D389.Documentation/Data Migration
D380.Documentation/Backup&Restore
D391.Documentation/Monitoring
D392.Documentation/DR
D393.Documentation/Support
D394.Documentation/Users
D395.Documentation/Operations
D396.Documentation/Training
D397.Documentation/Continuity Plan
D398.Documentation/Change Management
D399.---
D401.Media
D402.Media/Resources
D403.Media/Resources/Prompts
D404.Media/Resources/Instructions
D405.Media/Resources/Inline Tips
D406.Media/Resources/Online Assistance
D407.Media/Resources/Messages
D408.---
D409.---
D411.Media/Content
D412.---
D413.---
D421.Data
D422.Data/Legacy
D423.---
D424.---
D401.Environments
D402.Environments/General
D403.Environments/Integrations
D404.Environments/SecuredData
D405.Environments/TestData/BT
D406.Environments/TestData/DT
D407.Environments/TestData/ST
D408.Environments/TestData/UT
D409.Environments/TestData/IT
D410.Environments/TestData/TR
D411.Environments/ProdData/PP
D412.Environments/ProdData/PR
D413.---
D414.---
D421.Services
D422.Services/ALM
D423.Services/ALM/Wiki
D424.Services/ALM/Kanban
D425.Services/ALM/Repository
D426.Services/ALM/Secure Storage
D427.Services/ALM/Delivery Pipeline
D428.Services/ALM/Delivery Pipeline/Svc Account
D429.Services/ALM/Delivery Pipeline/Infrastructure Creation
D430.Services/ALM/Delivery Pipeline/Compilation
D431.Services/ALM/Delivery Pipeline/Packaging
D432.Services/ALM/Delivery Pipeline/Deployment
D433.Services/ALM/Delivery Pipeline/Configuration
D434.Services/ALM/Delivery Pipeline/Backup&Restore Automation
D435.Services/ALM/Delivery Pipeline/Schema Update Automation
D436.Services/ALM/Delivery Pipeline/QA Automation/Static
D437.Services/ALM/Delivery Pipeline/QA Automation/Dynamic
D438.Services/ALM/Delivery Pipeline/Data Migration Automation
D439.---
D440.---
D441.Services/Infrastructure
D442.Services/Infrastructure/DNS
D443.Services/Infrastructure/Email
D444.Services/Database Schemas&Seeding
D445.---
D446.---
D451.Services/Configuration
D452.---
D453.---
D461.Services/Server
D462.Services/Server/Middleware/AAA
D463.Services/Server/Middleware/Routing
D464.---
D465.---
D471.Services/Server/Controllers
D472.Services/Server/Controllers/Validation
D473.---
D474.---
D481.Services/Server/Services
D482.Services/Server/Services/Integration
D483.Services/Server/Services/Domains
D484.---
D485.---
D491.Services/Server/Common/Models
D492.Services/Server/Services
D493.---
D494.---
D501.Services/API/Gateway
D502.--
D503.--
D511.Services/Server/Client/API
D513.---
D514.---
D523.Services/Server/Client/UX
D524.Services/Server/Client/UX/Views
D525.Services/Server/Client/UX/Controllers
D526.Services/Server/Client/UX/Services
D527.Services/Server/Client/UX/Models
D528.---
D529.---
D541.Services/CorporateSiteIntegration
D542.Services/CorporateAPIGateway
D543.Services/ETL/Data Migration/Legacy-In
D544.Services/ETL/Data Migration/DW-Out
D545.---
D546.---

## REQ-TEMPLATE
Back to Table of Contents
Read the INSTRUCTIONS Tab First!
Entries entered in the following order: DT01.Role Description, DT02.Role Main Tasks, DT10.Prerequisites (Setup), DT20.Prerequisites (Info), DT30.Deliverables (Final), DT40.Deliverables (Enabling), DT50.Tasks, DT60.Responsibilities, DT70.Guidance,DT80.Desires
As a <ROLE> my Role is
As a <ROLE> my primary Tasks/Deliverables include:
PHASE | DELIVERABLE | CONCERN.ID | CONCERN.UNIQUEPATH | UID | TITLE | RISK | MITIGATION | RESPONSIBLE | BENEFITING | TYPE
P07.Desires |  | R00.01.01 | Risk/Title | 07.00.01.01 | Title

## Delivery
Back to Table of Contents
Read the INSTRUCTIONS Tab First!
Entries entered in the following order: DT01.Role Description, DT02.Role Main Tasks, DT10.Prerequisites (Setup), DT20.Prerequisites (Info), DT30.Deliverables (Final), DT40.Deliverables (Enabling), DT50.Tasks, DT60.Responsibilities, DT70.Guidance,DT80.Desires
As a <ROLE> my Role is
As a <ROLE> my primary Tasks/Deliverables include:
PHASE | DELIVERABLE | CONCERN.ID | CONCERN.UNIQUEPATH | UID | TITLE | RISK | NOTES | MITIGATION | RESPONSIBLE | BENEFITING | TYPE
P04.Direction |  | R00.01.01 | Risk/Vendor IP Lockin | 04.00.01.01 | Vendor IP Lockin | The vendor uses a proprietary ALM to manage workitems. |  | Use a cloud hosted ALM provided by the organisation. | S00.Procurement | S01.ALL
P04.Direction |  | R00.01.02 | Risk/Vendor Service Lockin | 04.00.01.02 | Vendor Service Lockin | The vendor uses services they've procured. | Whether it be their repositories, infrastructure, automation services, notification services, directory services (DNS), certification services -- they are all a significant migration risk in terms of possibility of transference, cost and time to do so.
P04.Direction |  | R00.01.03 | Risk/No public WorkItem board | 04.00.01.03 | No public WorkItem board | An ALM is available for development, but not for service consumers to view and/or contribute to. | A lack of feedback channel ensures the service receives none, therefore cannot be improved iteratively.
|  | R00.01.04 | Risk/No ALM for WorkItem Mgmt | 00.01.04 | No ALM for WorkItem Mgmt | WorkItems are managed using inappropriate services (eg: Confluence) or inappropriate/primitive/incomplete services (eg: JIRA)
|  |  | Risk/No ALM Documentation service |  | No ALM Documentation service | No Wiki is provided for Documentation of Discovery, Definition, Design, Delivery, Development notes

## Design
Back to Table of Contents
Read the INSTRUCTIONS Tab First!
Entries entered in the following order: DT01.Role Description, DT02.Role Main Tasks, DT10.Prerequisites (Setup), DT20.Prerequisites (Info), DT30.Deliverables (Final), DT40.Deliverables (Enabling), DT50.Tasks, DT60.Responsibilities, DT70.Guidance,DT80.Desires
As a <ROLE> my Role is
As a <ROLE> my primary Tasks/Deliverables include:
PHASE | DELIVERABLE | CONCERN.ID | CONCERN.UNIQUEPATH | UID | TITLE | RISK | MITIGATION | RESPONSIBLE | BENEFITING | TYPE
P10.Design |  | R00.01.01 | Risk/Design/Roles & GroupRoles | 10.00.01.01 | Design/Roles & GroupRoles | The use of system wide roles is inapropriate only in simple internal enterprise systems, whereas providing Group specific Roles represents real world users with more fidelity.
|  |  | Risk/Design/Permissions & Roles |  | Design/Permissions & Roles | The use of Roles only is suitable for very simple interface facing tools, but inappropriate for external facing services, being unable to represent the myriad ways roles can be developed.
|  |  | Risk/Design/Development Framework |  | Design/Development Framework | The choice of development framework may make development easier, at the expense of removing the possibility of Permssion based development, and/or Users belonging to multiple Roles within multiple Groups
|  |  | Risk/Design/Invitation |  | Design/Invitation | The lack of a means to send Invitiations to Roles within Groups means Provision must be managed in another (generally expensive) way.
|  |  | Risk/Design/T&Cs |  | Design/T&Cs | A service that provides Roles without enforcing the acceptance of T&Cs puts itself in legal jeopardy due to not having disclosing/specifying expectations and/or constraints.